## Course Management
| Curriculum Management System | Product Backlog with Sprint Summaries |  |  | Personal Software Process Fall 15
| GCIS-6340A-3 |  |  |  | Completed: 12/16/15
|  | Item | Last Update
|  | Main Backlog Items: | 2015-11-22
|  | Main Backlog Priority | 12/162015
|  | Sprint Logs: | 2015-12-16
Sprints
ID | Sprint Title | Start Date | End Date | Status | Notes
1 | Sprint 1 | 2015-11-14 | 2015-11-20 | Completed
2 | Sprint 2 | 2015-11-22 | 2015-12-08 | Completed | Reviewed with Dr. Tang 12/8/15
3 | Sprint 3 | 2015-12-08 | 2015-12-16 | Completed | Approved to begin by Tang 12/9/15
| Product Backlog | Top Level Features | Sprint 1 | Sprint 2 | Sprint3 | Sprint 4
ID | Priority (updated for Sprint 3) (high = 1) | Feature | 1: Status | 2: Status | 3: Status | 4: Status
0 | * | Test Cases, Documentation, Planning | Complete | Complete | Completed | Done
1 | 6 | Add New Major | N/A | Completed: Continued | Completed | Done
2 | 10 | Add courses | N/A | N/A | N/A | Waiting
3 | 2 | View/Modify curriculum | N/A | Completed: Continued | Completed | Done
4 | 3 | Remove/Add courses to curriculum | N/A | Completed: Continued | Completed | Done
5 | Complete | Change Password | Completed | Done | Done | Done
6 | 4 | Design | Completed: Cont. to S-2 | Completed: Continued | Completed; Continued | Waiting
7 | 8 | Add New Curriculum | N/A | Completed: Continued | Completed; Continued | Waiting
8 | 1 | Add Description Tracking | Incomplete: Cont. to S-2 | Completed: Continued | Completed | Done
9 | 7 | View and Modify Major | N/A | N/A | Completed | Done
10 | 11 | Add Prerequisites to Courses | N/A | N/A | N/A | Waiting
11 | 5 | Sort and Search | N/A | Completed: Continued | Partially Completed; Continued | Waiting
12 | 9 | Add Site Update Info | N/A | Completed: Continued | Completed | Done
Sprint 1 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes
1 | Meet to discuss goal | 0 | Abdulrahman Alhazmi Abdulrhman hadaddi Rayan Binlajdam Bhavik Moradiya | Completed
2 | Add description Tracking | 8 | Abdulrhman hadaddi, Bhavik Moradiya | Incomplete: Cont. to S-2 | All subtasks remained incomplete. Continued to Sprint 2
3 | Change Password | 5 | Abdulrahman Alhazmi | Completed
4 | Design Layout | 6 | Rayan Binlajdam | Completed; Continued
Sprint 2 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1 | Add Description: Fix incorrect Page landing | 8 | Bhavik Moradiy, Marco Orlando | Completed
2 | Add Description: Create/ Implement new page | 8 | Bhavik Moradiy, Marco Orlando | Completed
3 | Add Description: New Table in database | 8 | Bhavik Moradiy, Marco Orlando, James Gruss | Completed
4 | Add Description: Combine new form with foundation framework | 6 & 8 | Bhavik Moradiy, Marco Orlando | Incomplete | Add Description Form not merged with Foundation Framework | Hinderances: GitHub problems, Merging not realistic while creating form, Nate Carlin is in Swedan
5 | Design: Global Foundation Framework | 6 | Rayan Binlajdam, Carlin | Incomplete | Login.php is the only page implementing Foundation Framework | Hinderances: GitHub problems, Merging not realistic while others edit, Nate Carlin is in Swedan
6 | Design: Style Guide Implementation | 6 | Rayan Binlajdam, Carlin | Completed
7 | Add Courses to Curriculum: change table structure | 3 & 4 | Abdulrhman Hadaddi | Completed
8 | Add Courses to Curriculum: Sort by semesters (spring, fall, both) | 3 & 4 | Abdulrhman Hadaddi | Completed
9 | Add Courses to Curriculum: Add Search bar | 3 & 4 | Abdulrahman Hadaddi | Completed
10 | Add Courses to Curriculum: Change "Add more Course" and "View Courses" link to a button after new curriculum submission | 3 & 4 | Abdulrhman Hadaddi | Completed
11 | Add New Major: Take user directly to add curriculum after submission of major | 1 | Abdulrahman Alhazmi | Completed
12 | Add Courses to Curriculum: User Messaging Error and Success Messages | 3 & 4 | Abdulrahman Alhazmi, James Gruss | Completed
13 | Add Site Update Info & Site Picture | 12 | Bhavik Moradiy, James Gruss | Completed
14 | Test case for Add description | 8 & 0 | Marco Orlando | Completed
15 | Test Cases for Add New Major | 1 & 0 | James Gruss | Completed
16 | Test Cases For View / Modify Curriculum | 3 & 4 & 0 | James Gruss | Completed
17 | Final Testing and Documentation Finalization | 0 | James Gruss | Completed
18 | Test Cases for respective modules | 0 | All Members | Completed
Sprint 3 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Details
1 | Add Description: Change page name to "View / Update Description" | 8 | Bhavik; Jimmy | Completed
2 | Add Description: Change "add description" column to new name, only say "add description" for course records that do not have a description; courses with description should be view / update description. | 8 | Bhavik; Jimmy | Completed
3 | Add Description: new page to view description without opening updating form, with option to open editer. | 8 | Bhavik; Jimmy | Completed
4 | Add Description: edit the update description form page with information about the course being updated and merge page style | 8 | Bhavik; Jimmy | Completed
5 | Sort: Let user sort by more fields (semester, course code, course name) (Drop Down Menus?) | 3, 4, 11 | Abdul H; Marco | Partially Completed | Sort by semester; search by course code and name; Sort & Search do not work together
6 | Search: Let user search on more fields (semester, course code, course name) | 3, 4 | Abdul H; Marco | Partially Completed | Search by course code and course name; semester not searchable; Sort & Search do not work together
7 | Auto fill "Add New Curriculum" with Major after add new major submission | 1, 3, 7 | Abdul A; | Completed
8 | View Modify Major: More descriptive instructions on updating. | 1, 9 | Marco | Completed
9 | Design: Implement Foundation Framework | 6 | Nate Carlin; Rayan; James Gruss | Partially Completed | Main Structure done; tables in iframes need styled and made uniform
10 | Add Courses to Curriculum: Remove extra white space after selecting Course | 4 | Abdul A; Rayan. | Completed
11 | Put team info in site info page | 12 | Nate Carlin; Rayan | Completed
Approved By Dr. Tang on 12/9/15 during class time
Sprint 4 Backlog (Tentative)
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Details
1 | Sort by course code and course name | 11 |  | Waiting
2 | Search by semester | 11 |  | Waiting
3 | Unify filtering and sorting concurrently | 11 |  | Waiting
4 | Add Courses -> Remove extra space at top | 2 |  | Waiting
5 | Add Prerequistes to courses -> Give instructions on main landing page | 10 |  | Waiting
6 | Add Prerequistes to courses -> Remove ability to delete course OR make it a sub functionality, at the least | 10 |  | Waiting
7 | Add Prerequistes to courses -> Add edit/delete prerequiste functionality | 10 |  | Waiting
8 | Add New Curriculum-> submit -> take user directly to "selected courses" | 7 |  | Waiting