## Course Management
| Curriculum Management System | Sprint 2 Log and Backlog |  |  | Personal Software Process Fall 15
| GCIS-6340A-3 |  |  |  | Submission: 12/9/15
|  | Item | Last Update
| Note: Wrap up of Sprint 2 with backlog in its Sprint 2 form. | Main Backlog Items: | 2015-11-22
|  | Main Backlog Priority | 2015-11-23
|  | Sprint Logs: | 2015-12-08
Sprints
ID | Sprint Title | Start Date | End Date | Status | Notes
1 | Sprint 1 | 2015-11-14 | 2015-11-20 | Completed
2 | Sprint 2 | 2015-11-22 | 2015-12-08 | Completed | Reviewed with Tang on 12/8/15
3 | Sprint 3 | 2015-12-08
| Product Backlog | high to low ( 1 to 10 ) | Sprint 1 | Sprint 2 | Sprint3
ID | Priority: Updated at start of Sprint 2 | Feature | 1: Status | 2: Status | 3: Status
0 | * | Test Cases, Documentation, Planning | Complete | Complete
1 | 4 | Add New Major | N/A | Completed: Cont. to S-3 | TBA
2 | 7 | Add courses | N/A | N/A | TBA
3 | 8 | View/Modify curriculum | N/A | Completed: Cont. to S-3 | TBA
4 | 11 | Remove/Add courses to curriculum | N/A | Completed: Cont. to S-3 | TBA
5 | 2 | Change Password | Completed | Done | TBA
6 | 3 | Design | Completed: Cont. to S-2 | Incomplete: Cont. to S-3 | TBA
7 | 5 | Add New Curriculum | N/A | Completed: Cont. to S-3 | TBA
8 | 1 | Add Description Tracking | Incomplete: Cont. to S-2 | Completed: Cont. to S-3 | TBA
9 | 12 | View and Modify Major | N/A | N/A | TBA
10 | 10 | Add Prerequisites to Courses | N/A | N/A | TBA
11 | 6 | Sort Depend on the Semester | N/A | Completed: Cont. to S-3 | TBA
12 | 9 | Add Site Update Info | N/A | Completed: Cont. to S-3 | TBA
Sprint 1 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes
1 | Meet to discuss goal | 0 | Abdulrahman Alhazmi Abdulrhman hadaddi Rayan Binlajdam Bhavik Moradiya | Completed
2 | Add description Tracking | 8 | Abdulrhman hadaddi, Bhavik Moradiya | Incomplete: Cont. to S-2 | Subtasks remained incomplete. Continued to Sprint 2
3 | Change Password | 5 | Abdulrahman Alhazmi | Completed
4 | Design Layout | 6 | Rayan Binlajdam | Completed; Continued
Sprint 2 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes from meeting on 12/6/15 | Notes upon later review 12/6/15
1 | Add Description: Fix incorrect Page landing | 8 | Bhavik Moradiy, Marco Orlando | Completed
2 | Add Description: Create/ Implement new page | 8 | Bhavik Moradiy, Marco Orlando | Completed
3 | Add Description: New Table in database | 8 | Bhavik Moradiy, Marco Orlando, James Gruss | Completed
4 | Add Description: Combine new form with foundation framework | 6 & 8 | Bhavik Moradiy, Marco Orlando | Incomplete | Add Description Form not merged with Foundation Framework | Hinderances: GitHub problems, Merging not realistic while creating form, Nate Carlin is in Swedan
5 | Design: Global Foundation Framework | 6 | Rayan Binlajdam, Carlin | Incomplete | Login.php is the only page implementing Foundation Framework | Hinderances: GitHub problems, Merging not realistic while others edit, Nate Carlin is in Swedan
6 | Design: Style Guide Implementation | 6 | Rayan Binlajdam, Carlin | Completed
7 | Add Courses to Curriculum: change table structure | 3 & 4 | Abdulrhman Hadaddi | Completed
8 | Add Courses to Curriculum: Sort by semesters (spring, fall, both) | 3 & 4 | Abdulrhman Hadaddi | Completed
9 | Add Courses to Curriculum: Add Search bar | 3 & 4 | Abdulrahman Hadaddi | Completed
10 | Add Courses to Curriculum: Change "Add more Course" and "View Courses" link to a button after new curriculum submission | 3 & 4 | Abdulrhman Hadaddi | Completed
11 | Add New Major: Take user directly to add curriculum after submission of major | 1 | Abdulrahman Alhazmi | Completed
12 | Add Courses to Curriculum: User Messaging Error and Success Messages | 3 & 4 | Abdulrahman Alhazmi, James Gruss | Completed
13 | Add Site Update Info & Site Picture | 12 | Bhavik Moradiy, James Gruss | Completed
14 | Test case for Add description | 8 & 0 | Marco Orlando | Completed
15 | Test Cases for Add New Major | 1 & 0 | James Gruss | Completed
16 | Test Cases For View / Modify Curriculum | 3 & 4 & 0 | James Gruss | Completed
17 | Final Testing and Documentation Finalization | 0 | James Gruss | Completed
18 | Test Cases for respective modules | 0 | All Members | Completed
19 | Add indication that the site has been updated on main page | 12 | James Gruss | Completed
Sprint 3 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Notes upon review 12/6/15